## Contribution
StudentName | RequirementAnalysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management
Haotian Wu | Add following requirement: Quit game Restart game Destroy small objects on the map Let tank speed up |  |  | Responsible for "Requirement Analysis" part in the presentation of Iteration 0. "Tank creation and movement" and "Camera" part in the presentation of Iteration 1. | Commit: push the code of basic demo map design, adding new tank, implementation of camera script | Manual testing on basic map demo, tank movement and camera set up. |  | During the actual implementation, our team is sperated to 3 pairs. I worked with Qiwei Zheng on learning the basic map design and creation, implementing tank movement and camera movement. During the time working with QiweiZheng, it was awsome. We learned different parts and taught each other which makes the whole implementing process move fast. We also give Baoxiang Yang and LinlanChen some basic map design knowledge support so that they can ramp up quickly and start to create more fancy maps rather than the basic demo map. Inform every member about our code change in time to reduce the time of resolving conflicts.
Linlan Chen | Add following requirement: Deal damage to enemy Upgrade the tank Change skin of tank |  |  |  | Commit: Push the code of forest map and destroyed city map. Documentations. |  |  | Dicuss with Baoxiang about the map thing and work together to find new assets, new models, materials and textures. We decide the theme of our scenes, realistic or cute. We also discussed on how to construct the terrains and combine the models.
Baoxiang Yang | Add following requirement: Select Different Maps Function Tank Direction Turn and movement Record Scores for players |  |  |  | Commit: Desert Map |  |  | As the team leader, I hold the weekly meeting each week. Scheduled and rescheduled the meeting on a right time when everybody could take part in. As the meanwhile, I am responsible for keeping sync for different branches, hold meeting for merging everyone's code. During iteration1, our team sperated into 3 parts, as a product manager, I tried to seperated the tasks into 3 different parts and splited into 3 groups, each with 2 persons. Keep sync with members in groups every week and in the final week merge everything together.
Qiwei Zheng | Add following requirements: pause/unpause the game map boundary restriction Tank firing function tank movment function |  |  |  | Commit: pushed the code of basic demo map design, adding new tank, implementation of tank movement and camera script |  |  | Worked with Haotian Wu on the implementation of tank control and camera control as well as the basic demo map. I got familier with unity first and helped other team memebers when they encounted road blocks. Tested possible implementation and discuss with other leaders.
Shuhan Liu | Add following requirement: Hide tank behind objects Add HP of the tank Destroy the tank |  |  |  | Commit: Add shooting function Merge branch and resolve conflict Update shell speed |  |  | Worked on designing the implementation of the fire function of the tank. Discussed with teammates how to deal with the on trigger event when the tank hits an object, and also understand teammates' expectation on the fire funtion, which saves a lot of time when designing the function. Moreover, worked with team leader to choose the right graphic effect of the shell.
Lei Yang | Add following requirement: Clean unnecessary files in Github workspace Tank game start menu Unit test and test coverage calculation Metrics for test and work |  |  |  | Commit: Add firing system Clean Github code base, manage branch merge and resolve conflicts Add unit test coverage |  |  | Worked on researching firing system of the tank. Managed code base and configuration problems. Implemented automation ways to clean code base. Resolved severe commits conflicts in Github collaboration.

## Baoxiang Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 | 6(Decided the project topic) | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 6 | 4 | 2 | 2000-05-02 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 5，6 | 6
09/27 - 10/04 | 8 | 6 | 2 | 0 Learn unity. 1 Requirement analysis on meeting. 3. Implement Maps | 3 | 2 |  | 3 |  |  |  | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 0 Learn Unity. 2. Design Map 5 Communication | 3 |  | 3 |  |  | 2 |  | 2000-05-02 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 Learn Unity. 2. Design Maps. 3. Implement Maps 5 Communication | 2 |  | 2 | 2 |  | 2 |  | 0,2, 3,6 | 8
10/19 - 10/25 | 7 | 5 | 2 | 6 Arrangemen. 2. Design Maps. 3. Implement Maps 5 Communication | 0 |  | 1 | 2 |  | 2 | 2 | 2, 3, 5, 6 | 8
10/26 - 11/01 | 7 | 5 | 2 | 6 Arrangement. 2. Design Maps. 3. Implement Maps 5 Communication | 0 |  | 1 | 2 |  | 2 | 2 | 0,2, 3,6 | 8
11/02 - 11/ 08 | 8 | 6 | 2 | 6 Arrangement. 2. Design Maps. 3. Implement Maps 5 Communication | 0 |  | 1 | 2 |  | 2 | 2 | 2, 3, 5, 6 | 8

## Lei Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 8 | 6 | 2 | 6(Decided the project topic) | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 6 | 2 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - test existing shell system 5 - Discussion and collabrate 0 - Research firingshell system 3 - Fix terrin bug | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0, 3, 4, 5
10/16 - 11/01 | 7 | 5 | 2 | 4 - Testing fighting mechanism 5 - Discussion and collabrate 3 - Add health slider for tank | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0, 3, 4, 5
11/02 - 11/08 | 8 | 6 | 2 | 0 - Improve damage algorithm accuracy 3 - Fix existing bugs for damage algorithm 5 - Prepare for the presentation | 3 | 0 | 0 | 2 | 0 | 2 | 0 | 0, 3, 4, 5

## Haotian Wu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 10
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn map design tool 2 - Design the maps 3 - Create the maps, add different objects(trees, houses and etc). Implement the movement of Tank. 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to camera movement 3 - Implement the camera set up (focus, auto zoom in/out) 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - Find terrain bug during testing. 5 - Conmmunicate with team members about the bug. 0 - Learn more about terrain. 3 - Fix bug. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5
10/26 - 11/01 | 7 | 5 | 2 | 4 - Find tank go through objects bug and shell explodes inside box collider bug during testing. 5 - Communicate with team members about the bug. 0 - Learn more about rigidbody, collider and collision detector. 3 - Fix bugs. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5
11/02 - 11/ 08 | 8 | 6 | 2 | 0 - Learn about game manager implementation and game UI 3 - Start to implement game manager script. 5 - Communicate with other team members. | 4 | 0 | 0 | 1 | 0 | 3 | 0 | 0, 2, 3 ,5

## Qiwei Zheng
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 3 | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 | 1 | 0, 1, 3, 5 | 10
09/27 - 10/03 | 8 | 4 | 4 | 0- learned unity setup and model importing. learned pivotal tracker 1- More detail requirement design. 5 - basic tasks dispatching. | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 2- designing the maps and user interface 3 - create the maps and the add tank movement control 5 - merge changes | 0 | 0 | 3 | 3 | 0 | 2 | 0 | 3,6 | 8
10/12 - 10/18 | 8 | 6 | 2 | 3 - writing scripts for camera movement 5 - merge changes | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - testing moving function and map boundary. 5 - Discussion and collabrate 0 - Research on terrin collider. 3 - Fix terrin bug | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0, 3, 4, 5
10/16 - 11/01 | 7 | 5 | 2 | 4 - Testing fighting function and map boundary. 5 - Discussion and collabrate 3 - move tanks and camera on to the new map and fix tank shell bugs | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0, 3, 4, 5
11/02 - 11/08 | 8 | 6 | 2 | 0 - Learn about game manager implementation and game UI 3 - Start to implement game manager script. 5 - Prepare for the presentation | 3 | 0 | 0 | 2 | 0 | 2 | 0 | 0, 3, 4, 5

## Linlan Chen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0,1,5,6 | 6
09/18 - 09/22 | 6 | 4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5,6 | 6
09/27 - 10/04 | 7 | 3 | 4 | 0 - Learn Unity set up and how to input projects and models. Follow the tutorials and play with the assets to get more familiar with Unity. Learn to use Pivotal Tracker and have a basic understanding of the process of project management. 1 - Detailed requirements analysis. 6 - Some documentation. | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0,1,6 | 8
10/4 - 10/11 | 8 | 6 | 2 | 0 - Learn Unity development tools 2 - Do design based on user stories 5 - Communication 6 - Meeting Minutes | 3 | 0 | 2 | 0 | 0 | 2 | 1 | 0,3,5,6 | 8
10/12 - 10/18 | 8 | 6 | 2 | 3 - Implemented 2 map scenes 5 - Communication 6 - Meeting Minutes | 0 | 0 | 0 | 5 | 0 | 2 | 1 | 3,5,6
10/19 - 10/25 | 8 | 6 | 2 | 0 - Learn Unity test tools 5 - Discuss the map thing 6 - Meeting Minutes | 4 | 0 | 0 | 0 | 0 | 1 | 3 | 4,6
10/26 - 11/01 | 7 | 5 | 2 | 6 - Something wrong with my Unity Environment, spend whole week debugging Meeting Minutes | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 4,6
11/02 - 11/ 08 | 9 | 7 | 2 | 0 - Nunit and Ncover learning 4 - Unit test 5 - Communication 6 - Meeting Minutes | 3 | 0 | 0 | 0 | 4 | 2 | 1 | 4

## Shuhan Liu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 | 6(Decided the project topic) | [6 empty] | 6 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6 | 11
10/19 - 10/25 | 6 | 4 | 2 | 4 - Find shell bug. 5 - Conmmunicate with team members about the bug. 0 - Learn more about shell. 3 - Fix bug. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5 | 12
10/26 - 11/01 | 7 | 5 | 2 | 4 - Find shell can explode before shooting out. 5 - Communicate with team members about the bug. 0 - Changed the position of the shell shooting. 3 - Fix bugs. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5 | 12
11/02 - 11/ 08 | 8 | 6 | 2 | 0 - Added the shell shooting function for another bug 3 - Fixed the bug which shell can fly across the wall. 5 - Communicate with other team members. | 4 | 0 | 0 | 1 | 0 | 3 | 0 | 0, 2, 3 ,5 | 10