## Contribution
StudentName | RequirementAnalysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management
Haotian Wu | Add following requirement: Quit game Restart game Destroy small objects on the map Let tank speed up Resume game | Algorithm，Design Pattern |  | Responsible for "Requirement Analysis" part in the presentation of Iteration 0. "Tank creation and movement" and "Camera" part in the presentation of Iteration 1. "Requirement" part in the presentation of iteration 3. | Commit: push the code of basic demo map design, adding new tank, implementation of camera script. push the code of game manager, tank manager, ui design and scripts of main menu and pause menu. Also push some commits about some bug fixed. | Manual testing on basic map demo, tank movement, camera set up and menu. |  | During the actual implementation, our team is sperated to 3 pairs. I worked with Qiwei Zheng on learning the basic map design and creation, implementing tank movement and camera movement. During the time working with QiweiZheng, it was awsome. We learned different parts and taught each other which makes the whole implementing process move fast. We also give Baoxiang Yang and LinlanChen some basic map design knowledge support so that they can ramp up quickly and start to create more fancy maps rather than the basic demo map. Inform every member about our code change in time to reduce the time of resolving conflicts.
Linlan Chen | Add following requirement: Deal damage to enemy Upgrade the tank Change skin of tank Refine some acceptance tests of user stories. | Design Pattern, Classes and Methods | the documentation | Responsible for "testing" part in iteration 2 and iteration 3. | Commit: Push the code of forest map and destroyed city map. Documentations. Test code | Unit testing and test coverage calculation. Acceptance tests refine. |  | Dicuss with Baoxiang about the map thing and work together to find new assets, new models, materials and textures. We decide the theme of our scenes, realistic or cute. We also discussed on how to construct the terrains and combine the models. Discuss acceptance tests with the developers.
Baoxiang Yang | Add following requirement: Select Different Maps Function Tank Direction Turn and movement Record Scores for players | Introduction, Design Pattern |  |  | Commit: Desert Map |  |  | As the team leader, I hold the weekly meeting each week. Scheduled and rescheduled the meeting on a right time when everybody could take part in. As the meanwhile, I am responsible for keeping sync for different branches, hold meeting for merging everyone's code. During iteration1, our team sperated into 3 parts, as a product manager, I tried to seperated the tasks into 3 different parts and splited into 3 groups, each with 2 persons. Keep sync with members in groups every week and in the final week merge everything together.
Qiwei Zheng | Add following requirements: pause/unpause the game map boundary restriction Tank firing function tank movment function Object destruction feature | Class and Methods |  | iteration0: Overview, related work iteration1: iteration2: Map mechanism design final: User cases, Camera algorithm, screen capture videos. | Commit: pushed the code of basic demo map design, adding new tank, implementation of tank movement and camera script. Code for camera algorithm, object destruction code, playing area restriction. | Manual testing on game control, map area restriction and UI |  | Worked with Haotian Wu on the implementation of tank control and camera control as well as the basic demo map. I got familier with unity first and helped other team memebers when they encounted road blocks. Tested possible implementation and discuss with other leaders. prepare screen capture video for presentation
Shuhan Liu | Add following requirement: Hide tank behind objects Add HP of the tank Destroy the tank | Key Algorithms |  | Iteration0: QA iteration1: Tank shooting iteration2: Health and damgae final: Project Structure, Key algorithms | Commit: Add shooting function Merge branch and resolve conflict Update shell speed | Manual testing on tank shell firing to check if the shell explodes correctly, and if the damgae is dealt properly |  | Worked on designing the implementation of the fire function of the tank. Discussed with teammates how to deal with the on trigger event when the tank hits an object, and also understand teammates' expectation on the fire funtion, which saves a lot of time when designing the function. Moreover, worked with team leader to choose the right graphic effect of the shell.
Lei Yang | Add following requirement: Clean unnecessary files in Github workspace Tank game start menu Unit test and test coverage calculation Metrics for test and work | Design and architecture |  | Iteration0: Architecture design Iteration1: Tank fighting algorithm Iteration2: Tank health UI and damage final: Architecture, Design pattern | Commit: Add firing system Clean Github code base, manage branch merge and resolve conflicts Add unit test coverage | Execute block box unit test cases. Manually testing tank fighting system. |  | Worked on researching firing system of the tank. Managed code base and configuration problems. Implemented automation ways to clean code base. Resolved severe commits conflicts in Github collaboration.

## Baoxiang Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 | 6 - Decided the project topict | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0,1,5,6 | 6
09/18 - 09/22 | 6 | 4 | 2 | 5 - Schedule weekly meeting 6 - Decided the project details | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5,6 | 6
09/27 - 10/04 | 7 | 3 | 4 | 0 - Learn Unity set up and how to input projects and models. Learn to use Pivotal Tracker and have a basic understanding of the process of project management. 1 - Detailed requirements analysis. 6 - Documentations. | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0,1,6 | 8
10/4 - 10/11 | 8 | 6 | 2 | 0 - Learn Unity development tools 2 - Design based on user stories 5 - Split groups and assign tasks 6 - Weely meeting | 3 | 0 | 2 | 0 | 0 | 2 | 1 | 0,3,5,6 | 8
10/12 - 10/18 | 8 | 6 | 2 | 3 - Implemented the desert map scenes 5 - Schedule weekly meeting and group learn 6 - Meetings and documentations | 0 | 0 | 0 | 5 | 0 | 2 | 1 | 3,5,6 | 8
10/19 - 10/25 | 8 | 6 | 2 | 0 - Learn Unity Texture, materials 5 - Discuss the map thing 6 - Schdule weekly meeting and assign taks | 4 | 0 | 0 | 0 | 0 | 1 | 3 | 4,6 | 7
10/26 - 11/01 | 7 | 5 | 2 | 6 - Something wrong with my Unity Environment, spend whole week debugging and hold meetings | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 4,6 | 8
11/02 - 11/ 08 | 9 | 7 | 2 | 4 - design Forest 3 - Implement the new forest map 5 - Documentations and weekly meeting | 3 | 0 | 0 | 0 | 4 | 2 | 1 | 4 | 9
11/09 - 11/15 | 8 | 5 | 3 | 5 - Schdule weekly meeting and assign tasks 6 - Meeting minutes, class diagram | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 5,6 | 10
11/16 - 11/22 | 10 | 7 | 3 | 4 - design Airport 5 - Schdule weekly meeting and assign tasks 6 - Documentions | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 4,5,6 | 8
11/23 - 11/29 | 6 | 4 | 2 | 4 - design test cases, conduct part of system tests 5 - Schdule weekly meeting and assign tasks 6 - meeting minutes | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4,5,6 | 8
11/30 - 12/06 | 8 | 4 | 4 | 1 - Analyze the current bigs we have right now 2 - Design airplanes model 3 - Implement the new airport map 5 - Communicate with other team members | 0 | 0 | 0 | 0 | 3 | 4 | 1 | 4,6 | 8
12/07 - 12/13 | 9 | 5 | 4 | 4 - remained acceptance tests 5 - Schdule weekly meeting and assign tasks 6 - Documentations and fix bugs | 0 | 0 | 0 | 0 | 3 | 4 | 2

## Lei Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 8 | 6 | 2 | 6(Decided the project topic) | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 6 | 2 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - test existing shell system 5 - Discussion and collabrate 0 - Research firingshell system 3 - Fix terrin bug | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0, 3, 4, 5
10/16 - 11/01 | 7 | 5 | 2 | 4 - Testing fighting mechanism 5 - Discussion and collabrate 3 - Add health slider for tank | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0, 3, 4, 5
11/02 - 11/08 | 8 | 6 | 2 | 0 - Improve damage algorithm accuracy 3 - Fix existing bugs for damage algorithm 5 - Prepare for the presentation | 3 | 0 | 0 | 2 | 0 | 2 | 0 | 0, 3, 4, 5
11/09 - 11/15 | 7 | 4 | 3 | 0 - Learning about Canvas UI. 5 - Communicate with other team members. | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 0,2,3,5
11/16 - 11/22 | 7 | 4 | 3 | 2 - Designinga new airport map 3 - Implement the airport map 4 - Manual test fighting. 5 - Weekly meeting hold | 2 | 0 | 2 | 2 | 2 | 4 | 0 | 0,1,2,3,5
11/23 - 11/29 | 10 | 6 | 4 | 1 - Analyze the current bigs we have right now 2 - Design airplanes model 3 - Implement the new airport map 5 - Communicate with other team members | 3 | 1 | 2 | 4 | 0 | 6 | 0 | 2,3,5
11/30 - 12/06 | 10 | 6 | 4 | 2 - Update all damage algorithm 3 - Fixing bugs. 5 - Communicate with other team members. | 0 | 0 | 1 | 3 | 0 | 4 | 0 | 0, 1
12/07 - 12/13 | 7 | 4 | 4 | 0 - Prepare for final presentation 1 - Fix existing bugs | 3 | 4 | 0 | 0 | 0 | 0 | 0

## Haotian Wu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 10
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn map design tool 2 - Design the maps 3 - Create the maps, add different objects(trees, houses and etc). Implement the movement of Tank. 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to camera movement 3 - Implement the camera set up (focus, auto zoom in/out) 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - Find terrain bug during testing. 5 - Conmmunicate with team members about the bug. 0 - Learn more about terrain. 3 - Fix bug. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5
10/26 - 11/01 | 7 | 5 | 2 | 4 - Find tank go through objects bug and shell explodes inside box collider bug during testing. 5 - Communicate with team members about the bug. 0 - Learn more about rigidbody, collider and collision detector. 3 - Fix bugs. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5
11/02 - 11/ 08 | 8 | 6 | 2 | 0 - Learn about game manager implementation and game UI 3 - Start to implement game manager script. 5 - Communicate with other team members. | 4 | 0 | 0 | 1 | 0 | 3 | 0 | 0, 2, 3 ,5
11/09 - 11/15 | 8 | 6 | 2 | 0 - Keep learning about game manager implementation and game UI 3 - Keep implementing game manager script. 5 - Communicate with other team members. | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0,3,5
11/16 - 11/22 | 8 | 6 | 2 | 0 - Learning about Menu UI. 2 - Start to design Main menu. 3 - Fix several bugs. 5 - Communicate with other team members. | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 0,2,3,5
11/23 - 11/29 | 12 | 6 | 4 | 0 - Keep learning about Menu UI and start to learn menu controller. 2 - Keep designing main menu. 3 - Start to implement main menu script. 4 - Manual test menu. 5 - Communicate with other team members. | 2 | 0 | 2 | 2 | 2 | 4 | 0 | 0,1,2,3,5
11/30 - 12/06 | 14 | 8 | 6 | 0 - Start to learn about pause menu controller and how to connect map with menu. 1 - Analyze what requirment we finished. 2 - Design pause menu. 3 - Implement main menu script, pause menu script and fix bugs. 5 - Communicate with other team members | 3 | 1 | 2 | 4 | 0 | 6 | 0 | 2,3,5
12/07 - 12/13 | 8 | 4 | 4 | 2 - Update all menu design 3 - Fixing bugs. 5 - Communicate with other team members. | 0 | 0 | 1 | 3 | 0 | 4 | 0

## Qiwei Zheng
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 3 | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 | 1 | 0, 1, 3, 5 | 10
09/27 - 10/03 | 8 | 4 | 4 | 0- learned unity setup and model importing. learned pivotal tracker 1- More detail requirement design. 5 - basic tasks dispatching. | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 2- designing the maps and user interface 3 - create the maps and the add tank movement control 5 - merge changes | 0 | 0 | 3 | 3 | 0 | 2 | 0 | 3,6 | 8
10/12 - 10/18 | 8 | 6 | 2 | 3 - writing scripts for camera movement 5 - merge changes | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0, 2, 3, 6
10/19 - 10/25 | 7 | 5 | 2 | 4 - testing moving function and map boundary. 5 - Discussion and collabrate 0 - Research on terrin collider. 3 - Fix terrin bug | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0, 3, 4, 5
10/16 - 11/01 | 7 | 5 | 2 | 4 - Testing fighting function and map boundary. 5 - Discussion and collabrate 3 - move tanks and camera on to the new map and fix tank shell bugs | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0, 3, 4, 5
11/02 - 11/08 | 8 | 6 | 2 | 0 - Learn about game manager implementation and game UI 3 - Start to implement game manager script. 5 - Prepare for the presentation | 3 | 0 | 0 | 2 | 0 | 2 | 0 | 0, 3, 4, 5
11/09 - 11/15 | 7 | 4 | 3 | 3 - implement game manager in game scene 5 - Communication | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 3
11/16 - 11/22 | 6 | 3 | 3 | 3 - bug fixing 5 - weekly meeing and requirement adjustment | 0 | 0 | 0 | 3 |  | 3 | 0 | 3
11/23 - 11/29 | 10 | 7 | 3 | 0- learning invisibel wall implemnetation in Unity 1 - check on desired feature and optional feature 3 - add invisible wall to restrict playing area 5 - developing SDD document | 2 | 3 | 0 | 2 | 0 | 3 | 0 | 2017-03-04
11/30 - 12/06 | 13 | 7 | 6 | 3 - implement destructible object and fixed explosion rendering bug add camera adaptation to all maps 4 - testing on UI 5 - weekly meeting and requirement adjustment prepare for final presentaion | 0 | 0 | 0 | 5 | 2 | 6 | 0 | 2017-03-04
12/07 - 12/13 | 8 | 4 | 4 | 3 - implement object explosion damage to the tanks, UI minor adjustment 4 - final testing on UI 5 - prepare for final presentation | 0 | 0 | 0 | 3 | 1 | 4

## Linlan Chen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0,1,5,6 | 6
09/18 - 09/22 | 6 | 4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5,6 | 6
09/27 - 10/04 | 7 | 3 | 4 | 0 - Learn Unity set up and how to input projects and models. Follow the tutorials and play with the assets to get more familiar with Unity. Learn to use Pivotal Tracker and have a basic understanding of the process of project management. 1 - Detailed requirements analysis. 6 - Some documentation. | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0,1,6 | 8
10/4 - 10/11 | 8 | 6 | 2 | 0 - Learn Unity development tools 2 - Do design based on user stories 5 - Communication 6 - Meeting Minutes | 3 | 0 | 2 | 0 | 0 | 2 | 1 | 0,3,5,6 | 8
10/12 - 10/18 | 8 | 6 | 2 | 3 - Implemented 2 map scenes 5 - Communication 6 - Meeting Minutes | 0 | 0 | 0 | 5 | 0 | 2 | 1 | 3,5,6
10/19 - 10/25 | 8 | 6 | 2 | 0 - Learn Unity test tools 5 - Discuss the map thing 6 - Meeting Minutes | 4 | 0 | 0 | 0 | 0 | 1 | 3 | 4,6
10/26 - 11/01 | 7 | 5 | 2 | 6 - Something wrong with my Unity Environment, spend whole week debugging Meeting Minutes | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 4,6
11/02 - 11/ 08 | 9 | 7 | 2 | 0 - Nunit and Ncover learning 4 - Unit test 5 - Communication 6 - Meeting Minutes | 3 | 0 | 0 | 0 | 4 | 2 | 1 | 4
11/09 - 11/15 | 8 | 5 | 3 | 4 - Add more unit tests 5 - Communication 6 - Meeting minutes, class diagram | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 5,6
11/16 - 11/22 | 10 | 7 | 3 | 4 - design more acceptance tests and system tests 5 - communication 6 - meeting minutes, STD's unit test part. | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 4,5,6
11/23 - 11/29 | 6 | 4 | 2 | 4 - design test cases, conduct part of system tests 5 - communication 6 - meeting minutes | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4,5,6
11/30 - 12/06 | 8 | 4 | 4 | 4 - conduct acceptance tests 5 - communication 6 - STD's sytem testing part | 0 | 0 | 0 | 0 | 3 | 4 | 1 | 4,6
12/07 - 12/13 | 9 | 5 | 4 | 4 - remained acceptance tests 5 - communication 6 - STD's rest part | 0 | 0 | 0 | 0 | 3 | 4 | 2

## Shuhan Liu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 | 6(Decided the project topic) | [6 empty] | 6 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6 | 11
10/19 - 10/25 | 6 | 4 | 2 | 4 - Find shell bug. 5 - Conmmunicate with team members about the bug. 0 - Learn more about shell. 3 - Fix bug. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5 | 12
10/26 - 11/01 | 7 | 5 | 2 | 4 - Find shell can explode before shooting out. 5 - Communicate with team members about the bug. 0 - Changed the position of the shell shooting. 3 - Fix bugs. | 3 | 0 | 0 | 1 | 1 | 3 | 0 | 0, 3, 4, 5 | 12
11/02 - 11/ 08 | 8 | 6 | 2 | 0 - Added the shell shooting function for another bug 3 - Fixed the bug which shell can fly across the wall. 5 - Communicate with other team members. | 4 | 0 | 0 | 1 | 0 | 3 | 0 | 0, 2, 3 ,5 | 10
11/09 - 11/15 | 7 | 4 | 3 | 0 - Learning about Canvas UI. 5 - Communicate with other team members. | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 0,2,3,5
11/16 - 11/22 | 7 | 4 | 3 | 3 - Implemented functions in tank manager 4 - Manual test fighting. 5 - Weekly meeting | 2 | 0 | 2 | 2 | 2 | 4 | 0 | 0,1,2,3,5
11/23 - 11/29 | 10 | 6 | 4 | 3 - Changing the tank shooting method to make it more real 5 - Communicate with team members | 3 | 1 | 2 | 4 | 0 | 6 | 0 | 2,3,5
11/30 - 12/06 | 10 | 6 | 4 | 2 - Update all damage algorithm 3 - Adding Health bars on main canvas 5 - Communicate with other team members. | 0 | 0 | 1 | 3 | 0 | 4 | 0 | 0, 1
12/07 - 12/13 | 7 | 4 | 4 | 0 - Prepare for final presentation 1 - Fix existing bugs | 3 | 4 | 0 | 0 | 0 | 0 | 0